## GPI-Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Career Path Prediction and Guidance System
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 2026-02-02
EXPECTED COMPLETION DATE | 2026-02-15
ESTIMATED COST | N.A.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | The objective of this project is to develop a Career Path Prediction and Guidance System that helps students identify the most suitable career based on their academic performance, technical skills, and interests. The system will use Machine Learning and Deep Learning algorithms to analyze student data and predict appropriate career roles. The application will also provide personalized recommendations such as required skills, certifications, courses, and career roadmaps to guide students toward achieving their career goals. An interactive web application using Streamlit will be developed so that students can easily enter their profile details and receive career guidance.
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | Many students struggle to choose the right career path due to lack of proper guidance and awareness about industry requirements. Traditional career counseling methods are often manual and may not consider multiple factors such as academic performance, technical skills, and personal interests. This project aims to solve this problem by using data-driven machine learning models that analyze student attributes and predict suitable career paths. Benefits of the system include: Providing personalized career guidance to students Helping students understand required skills and certifications Supporting educational institutions in career counseling Using AI-driven insights to improve career decision-making
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | Performance Goal: Achieve prediction accuracy above 80% using machine learning models. Time Goal: Complete development and testing of the system within the project timeline . Resource Goal: Develop the system using Python, Machine Learning libraries, and Streamlit web framework with available computing resources. Success Metrics: Model accuracy and evaluation metrics (precision, recall, F1-score) Response time of predictions User satisfaction with recommendations Successful deployment of the web interface
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | The following deliverables will be produced at the end of the project: Software Requirement Specification (SRS) Document Dataset preprocessing and analysis report Machine Learning model implementation Deep Learning model implementation Model evaluation and comparison report Career prediction system Streamlit web application Final project report Project presentation
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | The following features are included in the project development: Student data input interface Data preprocessing and feature engineering Training multiple machine learning models Model evaluation and selection Career path prediction Personalized recommendation system Web interface using Streamlit Displaying recommended skills, courses, and certifications
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | The following features are not included in the initial version of the system: Integration with external job portals Real-time industry job market analysis Mobile application development Automatic resume generation Integration with university databases These features may be implemented in future versions of the system.
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | Number of Resources: 1 Project Developer: Shourya Malik– Responsible for system design, model development, implementation, testing,
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | Laptop / Computer system Python programming environment Machine learning libraries (Scikit-learn, TensorFlow) Streamlit framework Development tools (Jupyter Notebook / VS Code)
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | Estimated Costs: Development Cost: Software tools: Free (Open-source libraries)
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | Shourya Malik
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | Project Guide Project Evaluation Committee
END CUSTOMER (Mention the client name.) | Primary Users: Students seeking career guidance Secondary Users: Educational institutions and career counselors
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | Limited dataset size may affect prediction accuracy. Incorrect user inputs may produce inaccurate predictions. Model overfitting may reduce performance on new data.
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | The dataset provided by the team is accurate and reliable. Students will provide correct information while using the system. The dataset contains sufficient features for career prediction. Users will have access to a computer and internet connection.
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | Limited project development time. Dependency on dataset quality. Limited computational resources for deep learning training.
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | MILESTONE 1 – Requirement Gathering Completion Date: 02-02-2026 Understanding problem: Career Path Prediction System Collecting and studying dataset (Dataset.csv) Identifying features like: coding skills interests certifications Defining target variable: Suggested Job Role Finalizing system objective and scope
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | MILESTONE 2 – Planning Completion Date: 02-04-2026 Divided project into modules: preprocessing training evaluation app Selected ML & DL models
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | MILESTONE 3 – Design Completion Date: 02-04-2026 Designed ML pipeline (encoding + scaling) Planned model workflow Designed Streamlit UI
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | MILESTONE 4 – Development Completion Date: 02-10-2026 Implemented preprocessing.py Trained ML models (RF, SVM, Logistic, XGBoost) Built Deep Learning model Saved models
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | MILESTONE 6 – Testing Completion Date: 02-13-2026 Evaluated models (accuracy, precision, recall, F1) Selected best model Tested predictions
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | MILESTONE 7 – Deployment & Closure Completion Date: 02-15-2026 Integrated with Streamlit (app.py) Tested UI and outputs Generated predictions + recommendations Prepared final report & presentation
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide")