## Guide
IAC GLOBAL PROFESSIONAL INTERNSHIP
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Shourya Malik
Document Created On: | 2026-02-10
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop

## PROJECT SCHEDULED
PROJECT PLAN
DOCUMENT VERSION: 1.0 | [6 empty] | INSTRUCTION TO USE THE PROJECT PLAN TEMPLATE: • All fields must be duly filled • The tasks/ activities listed in the template are bare minimum tasks and are not exhaustive. You will be required to add tasks/ activities based on the technology and the respective problem statement. • Clear all the sample data provided in the template. The data provided is only for reference purposes. • Mention the features you are working on the ”task name” field. • Mention the resource name who is responsible for completing a particular feature in the “assigned to” field. • Mention the start date and end date of a particular feature in the “start date” and “end date” field respectively. • Mention the time duration for completing a specific task in the “duration in days” field. • Select the current status of the feature you are working on from the drop-down list provided in the “status” field.
PROJECT NAME | Machine Learning
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Career Path Prediction and Guidance System using ML/DL with a Streamlit interface.
PROJECT SCOPE | Analyze student data, train ML/DL models, and generate career recommendations.
PROJECT START DATE | 2026-02-02
PROJECT END DATE | 2026-02-15
OVERALL PROGRESS | Completed
Candidate Name | Shourya Malik
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem |  | 2026-02-02 | 2026-02-03 | 1 | COMPLETED
| 1.2 Recruit a team |  | 2026-02-02 | 2026-02-03 | 1 | COMPLETED
| 1.3 Create a project charter |  | 2026-02-02 | 2026-02-03 | 1 | COMPLETED
| 1.4 Requirement gathering |  | 2026-02-02 | 2026-02-03 | 1 | COMPLETED
2 Planning
| 2.1 Approval of business process |  | 2026-02-04 | 2026-02-05 | 1 | COMPLETED
| 2.2 Baseline project plan |  | 2026-02-04 | 2026-02-05 | 1 | COMPLETED
| 2.3 Team roles and responsibilities |  | 2026-02-04 | 2026-02-05 | 1 | COMPLETED
3 Execution
| 3.1 Finalize design |  | 2026-02-06 | 2026-02-09 | 3 | COMPLETED
| 3.2 Build |  | 2026-02-06 | 2026-02-09 | 3 | COMPLETED
| 3.2.1 Features |  | 2026-02-06 | 2026-02-09 | 3 | COMPLETED
Student Input Interface
sliders and dropdown menus for adding user data
Career Prediction
predicts the most suitable career path
Models used:
Random Forest
Logistic Regression
Support Vector Machine (SVM)
XGBoost
Deep Learning (TensorFlow)
| Model Selection |  | 2026-02-09 | 2026-02-10 | 1 | COMPLETED
| Career Recommendation System |  | 2026-02-09 | 2026-02-10 | 1 | COMPLETED
Career Recommendation System
Skills to develop
Certifications
Projects
Internship suggestions
Career roadmap
| User Interface |  | 2026-02-11 | 2026-02-12 | 1 | COMPLETED
Header and navigation layout
Student profile input panel
Prediction result display
Recommendation tabs
Learning Path Tabs
Courses & Skills
Projects & Certifications
| Internships & Career Roadmap |  | 2026-02-12 | 2026-02-13 | 1 | COMPLETED
Dataset Insights Section
Model Resource Management
Encoders, scalers, and trained models are saved using Joblib.
Deep learning model stored using .h5 format.
| 3.3 Testing |  | 2026-02-14 | 2026-02-15 | 1 | COMPLETED
3.3.1 Automation testing
| 4 Closure |  | 2026-02-15 | 2026-02-15 | 1 | COMPLETED