## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Machine Learning
INTERN NAME: | Shourya Malik
PROJECT NAME: | Career Path Prediction and Guidance System
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2026-02-28
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Career Path Prediction and Guidance System
PROJECT ID | IP-11010
PROJECT MANAGER | HARSHADA TAPOLE
PROJECT SPONSOR | TUSHAR TAPOLE
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2026-02-11 | Difficulty in understanding dataset structure and features during initial phase | Data Understanding | Yes | Perform proper data exploration and understand dataset columns before starting model training | Conducted Exploratory Data Analysis (EDA) using Pandas and visualizations | Project Developer | Solved | Helped improve understanding of features affecting placement
2 | 2026-02-18 | Model accuracy was low during first training attempt | Model Development | Yes | Apply feature engineering and test different algorithms to improve accuracy | Added new features and retrained model using improved dataset | Project Developer | Solved | Accuracy improved after feature engineering
3 | 2026-02-20 | Difficulty integrating prediction output with result display | System Integration | No | Design output format before implementing prediction logic | Modified output format and improved result display | Project Developer | Solved | Final prediction results became clearer
4 | 2026-02-23 | Time management challenge during final project implementation | Project Management | Yes | Plan development phases and follow a structured schedule | Created task plan and completed remaining modules step by step | Project Developer | Solved | Helped complete project before deadline