## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://script.google.com/macros/s/AKfycbz1vCRZzDZf9SkwX8gv1DzKe59fupHWWehSUu0jeTsiZZxn3YdNVAD1sHDLDUanbJ5O/exec | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 4 | 0 | 0 | 0 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | Carrer Prediction & Guidance System |  | Project Id: | IP-11038 | Project Manager: | Harshada Topale |  |  | Assumption | 1 | 0 | 0 | 1 | 0 | 0
[10 empty] | Issue | 2 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: | 1 |  | Last Updated date: | 2026-02-15 | Project Team Lead: | ABC |  |  | Dependency | 1 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 8 |  |  |  |  | 1
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Insufficient or poor-quality dataset | May reduce model accuracy and affect prediction results | Perform data cleaning, preprocessing, and feature engineering | Project Developer | High | 8 | Closed | Risk
2 | Risk | Model overfitting | Poor prediction on new data | Cross Validation Is used | Project Developer | High | 7 | Closed | Assumption
3 | Risk | Low confidence predictions | Unclear career recommendations | Added recommendation system to support predictions | Project Developer | Moderate | 6 | Closed | Issue
4 | Risk | Feature overlap between careers | Incorrect or confusing predictions | Performed feature importance and correlation analysis | Project Developer | High | 7 | Closed | Dependency
5 | Issue | Delay in preprocessing and data cleaning | Project timeline delay | Managed time with buffer and modular coding | Project Developer | Moderate | - | Closed
6 | Issue | Errors during model loading in Streamlit | App not running properly | Fixed path issues and ensured model saving/loading consistency | Project Developer | High | - | Closed | Open
7 | Assumption | Dataset is accurate and reliable | Model depends heavily on data quality | Verified dataset before training | Project Developer | Moderate | 6 | Open | Closed
8 | Dependency | Libraries (scikit-learn, TensorFlow, Streamlit) | Project depends on external tools | Used stable versions and tested environment | Project Developer | High | 7 | Closed
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24